## Sheet1
TIME ESTIMATE | ASSIGNED DATE | FINISH DATE | TASK | ASSIGNED | DETAILS
2 Hour | 2013-06-12 | 2013-06-12 | Implement a Home screen | Shuwen
1 Hour | 2013-06-13 | 2013-06-13 | Add a “Play” button to play the game | Shuwen
5 Hour | 2013-06-11 | 2013-06-11 | Implement a Game Play screen | Shuwen
1 Hour | 2013-06-06 | 2013-06-06 | Install Emulator software on all developer devices | Shuwen
2 Hour | 2013-06-12 | 2013-06-12 | Implement Geolocation API | Shuwen
3 Hour | 2013-06-13 | 2013-06-13 | Implement a Player object mapping the player’s position on the game map to the Game Play screen | Shuwen
3 Hour | 2013-06-12 | 2013-06-12 | Test caseses | Hongyi