## Iteration 2
TIME ESTIMATE | ASSIGNED DATE | FINISH DATE | TASK | ASSIGNED | DETAILS
Display Coin
1 day | 6/20/2013 | 6/23/2013 | Implement coin class | Hongyi
1 day | 6/28/2013 |  | Debug, coin and location functions | Hongyi
1 day |  |  | Link coin display on map
Network Connection
1 day | 6/20/2013 | 6/24/2013 | Implement server player | Shuwen
1 day | 6/20/2013 | 6/28/2013 | Implement server network | Shuwen
1 day | 6/28/2013 |  | Implement client network
Update Location
1 day | 6/20/2013 | 6/23/2013 | Refactor location handling | Shuwen
1 day |  |  | Improve player display
1 day |  |  | Refator map handling function
1 day |  |  | send location over network
GUI Display
1 day | 6/19/2013 | 6/20/2013 | Test case, screen switch from Hone screen to play screen | Shuwen
1 day |  |  | Create Tutorial script | Cagri
1 day | 6/19/2013 |  | Implement Tutorial screens with Next, Back, and Exit buttons to traverse and exit the tutorial screens | Cagri
1 day |  |  | Link Exit Tutorial button to User Profile screen | Cagri
1 day |  |  | Link Tutorial screens Next, and Back buttons to proceding, and preceding Tutorial screen respectively where applicable. | Cagri
1 day |  |  | Create place holder arts | Cagri
1 day |  |  | Code algorithm for calculating amount of Gold Coins and Treasure objects specific to a given game based on the number of active users.
1 day |  |  | Code algorithm for appropriate generation and placement of Gold Coin, Treasure, and Ghost objects within randomized geofences within the game map and Ghost-Zone boundaries
1 day |  |  | Implement Action screens with appropriate user inuput objects and application response for Gold Coins and Treasure
1 day |  |  | Link Game Play screen to Gold Coin and Treasure Action screens
1 day |  |  | Link Gold Coin and Treasure Action screens to Game Play screen
1 day |  |  | Code algorithm for application response and actions upon user encountering Gold Coins and Treasure
1 day |  |  | Code algorithm for updating Collected Treasure Value display, Player Life meter, Remaining Treasure display, Time Remaining Clock values on the database and on the application Game Play Screen.
1 day |  |  | Code algorithms for user action/input upon encountering Gold Coins and Treasure
1 day |  |  | Code algorithm for communication between application and database via the server upon user action/input during game play (ex. Gold Coin/Treasure depletion, player life depletion/ death/ expulsion from game due to exiting game map boundaries.