## Sheet1
TIME ESTIMATE | ASSIGNED DATE | FINISH DATE | TASK | ASSIGNED | DETAILS
Coin Generation
1 day | 2013-07-11 | 2013-07-12 | Server can track all playing players(join/quit) | Shuwen
3 day | 2013-07-11 | 2013-07-21 | Server can generate coins within the hill area | Hongyi | pair programing to slove the problem
1 day | 2013-07-20 | 2013-07-24 | Server can store coins within a game board | Hongyi
Coin Collection
1 day | 2013-07-12 | 2013-07-19 | Client will send all moving actions to the server | Shuwen
1 day | 2013-07-18 | 2013-07-21 | Server can recive all players location update packets | Shuwen
1 day | 2013-07-11 | 2013-07-24 | Server can calculate player location with nearest coin location | Hongyi
1 day | 2013-07-20 | 2013-07-24 | Server can sent coin packet when a player close to a coin | Shuwen
1 day | 2013-07-11 | 2013-07-24 | Server can save the amount of coin that a player collected | Hongyi
Coin Display
1 day | 2013-07-18 | 2013-07-19 | Server can sent lastest status of coin collection to client | Shuwen
1 day | 2013-07-20 | 2013-07-22 | Client can recive coin status from server | Shuwen
1 day | 2013-07-22 | 2013-07-23 | Client can display the coin status in game play screen | Shuwen
2 hours | 2013-07-24 | 2013-07-25 | combine all works togeter | Hongyi Shuwen